## Slide 1: MEASURE L BOND PROGRAM
CITIZENS’ BOND OVERSIGHT COMMITTEE
April 01, 2014
PROGRAM UPDATE

## Slide 2: Role of Committee
Education Code Section 15278
  Inform the public concerning expenditures
  Advise the public in compliance with Prop 39 requirements
  Ensure that bond revenues are expended according to Prop 39 requirements
  Ensure that no funds are used for teachers’ or administrators’ salaries or operating expenses

## Slide 3: Measure L – Voter Approved Nov. 2012- $150M General Purpose & Scope
Repair and modernize aging classrooms and schools
Bring existing structures up to safety and access codes
Expand educational opportunities to students
Enhance health and safety of school sites
Modernize classroom technology

## Slide 4: Role of Committee
Education Code Section 15278
  Inform the public concerning expenditures
  Advise the public in compliance with Prop 39 requirements
  Ensure that bond revenues are expended according to Prop 39 requirements
  Ensure that no funds are used for teachers’ or administrators’ salaries or operating expenses

## Slide 5: Board adopted prioritization criteria
Prioritizing Project Scope and Needs District Wide
1. Life Health Safety and code compliance items always come first.
Definition for Life Health Safety:
Any identified issue that represents a threat to the safety or health of students, staff and administration within the context of the bond approved language. This definition includes potential loss of telecommunications/paging/intercom that would prevent adequate communications during an emergency.
2. Projects that have pending leveraged funding sources with deadlines associated with them (within the context of the approved bond language). If we miss the deadline we potentially lose the funding.
3. Buildings/ Functions/ Scope that directly impact education and the academic performance
4. Key Infrastructure and District Wide Support (Food Services, Technology, utilities, mechanical systems etc.) that support the educational process and impact the learning environment and student health.
Buildings/ Athletic Fields and uses that are or will be highly utilized to maximum value and are of a key interest to the sites and/or community.
Scope and project needs that are eligible for leveraged funding beyond the Bond Program (State Funding, E-Rate, Joint Use, etc.).
7. Administrative areas that support educational functions and add value.
8. Out-door areas and play yards that add value.
Cosmetics I esthetic improvements.
Proposed scope that meet the approved bond language but is outside the original project intent and vision.

## Slide 6: Update on auditor selection
  COC sub-committee met in February to develop RFQ and interview process
  RFQ released and “on the street”
  Closes April 9
  COC sub-committee will oversee initial screening and interviews, and make recommendation to the committee
  COC to make final recommendation to the board in late May

## Slide 7: Bond program overview
  Over 50 projects (new construction, modernization, deferred maintenance, IT, and endowments) currently in process
  All bond program management has been brought in house
    Overseen by district staff
    New staff has been brought on board
  Program management firm was released in November

## Slide 8: Phase one project update
  Play Structures at 10 Sites-Complete
  School door locks- Northern and Central complete (16 sites)
  Aptos High School Water Tank-Under construction
  Aptos High School Bleachers-Under construction
  Aptos High School Freedom Field-Under Construction
  Renaissance High School Well-Complete
  Bradley IT network install-Complete (beginning Phase2 faster wireless and switches)
  Final stage of Aptos area IT upgrades
  District-wide IT infrastructure upgrades
  New carpeting at 11 school sites

## Slide 9: Projects – Updates
Play Structure Projects
  All Complete
School Door Locks
  All Elementary Schools-
  North and Central Complete South will be complete April 3, 2014
  Secondary School Bid being packaged for bid this spring
Video security surveillance systems at all secondary school sites under analysis and RFP development – install in summer/fall

## Slide 10: AHS water tank: Just about complete!

## Slide 11: Pajaro Middle School Kitchen

## Slide 12: Solar Projects
Construction underway Bradley and Hall District
  Start date March 5, 2014
  Scheduled completion April 22, 2014
Design work underway-for Aptos, Watsonville High and Rolling Hills Middle Schools DSA review in May

## Slide 13
 | Series A | Series B | Totals
Principal Amount | $68,540,000 | $11,460,000 | $80,000,000
Building Fund | $65,478,255 | $5,000,000 | $70,478,255
Technology Endowment |  | $2,500,000 | $2,500,000
Small Repair Endowment |  | $3,750,000 | $3,750,000
COP/Lease Payoff | $2,628,229 |  | $2,628,229
Debt Service Fund |  | $134,553 | $134,553
Cost of Issuance | $433,516 | $75,447 | $508,963
Totals | $68,540,000 | $11,460,000 | $80,000,000
Summary of Bond Activity

## Slide 14: Work Areas
The district identified 3 “Work Areas” which forms the structure for project tracking. All future reports and updates will follow this format:
  North – Aptos Area
  Central – Pajaro Area
  South – Watsonville Area

## Slide 15
Expenditures By Area
As of February 28th 2014
North- APTOS AREA | Budget | Spent YTD | Remainder | % Spent
TOTALS | $29,627,958 | $1,892,318 | $28,601,836 | 6.39%
Central PAJARO | Budget | Spent YTD | Remainder | % Spent
TOTALS | $34,881,171 | $1,309,312 | $34,187,650 | 3.75%
South WATSONVILLE | Budget | Spent YTD | Remainder | % Spent
TOTALS | $54,446,728 | $738,023 | $54,155,361 | 1.36%
Grand Totals | $118,955,857 | $3,939,653 | $116,944,847 | 3.31%

## Slide 16: Phase I North Area -Project Status
Description of Project | Status | Comments
Aptos High School-Freedom Field Phase II Modernization | Planning | 
Freedom Field-Phase I | Under Construction | Work Should be completed by end of June
Bleacher Replacement | Site complete; Bleachers in fabrication | Work should be completed end of April
Mar Vista Modernization/Reconfiguration | Planning | 
Mar Vista Modernization/Multi Purpose Room | Planning | 
Rio Del Mar ES Modernization | Planning | Site Meeting 9-3-13
Valencia ES Modernization | Planning | 
Renaissance HS Well | Complete | Water Testing

## Slide 17: Phase I Central Area- Project Status
Description of Project | Status | Comments
PVHS Auditorium | Planning | Work with Coastal Commission for their initial input
PVHS Playfields | Planning | Work with Coastal Commission for their initial input
Cesar Chavez MS Modernization | In Design | Schematic Design 90% Complete
Lakeview MS Modernization-Painting school and repairing roof leaks | In Design | Work should be completed over summer break
Rolling Hills MS Gym/Kitchen Modernization | Planning | 
Ann Soldo Modernization-Siding replacement, roof, doors and painting | In Design | Work should be completed over summer break

## Slide 18: Phase I Central Area- Continued
Description of Project | Status | Comments
Calabasas ES Modernization-Roof Repairs | In Design | Work should be completed over summer break
Freedom ES Modernization | In Design | Work should be completed over summer break
Radcliff ES Modernization | Planning | 
Alianza/WCSA-Fire Water Line | In Design | Schematic Design Complete
Quick Start Projects | In Planning | 
Flooring Project-Phase II | Bid Phase | Bid solicitation to occur week of 4/01/14

## Slide 19: Phase I South Area -Project Status
Description of Project | Status | Comments
Watsonville HS 2 Story New Classrooms | In Design | Schematic Design Complete
Pajaro MS Modernization-Includes new Kitchen site work and drainage | In Design | Schematic Design Complete and Approved
Hall District Modernization-Includes Repairs to D Wing, Gutter replacement and Trim Paint | In Design | Schematic Design 60% Complete
EA Hall MS New Classroom Building-9 new classrooms | In Design | Schematic Design 90% Complete
EA Hall MS Playfield Upgrades | In Design | Schematic Design 95% Complete
Mintie White Modernization-A-Wing | In Planning | 
Quick Start Projects | In Planning | 
Flooring Project-Phase II | Bid Phase | Bid solicitation to occur week of 4/01/14

## Slide 20: Measure L Bond Technology Projects Update
Dan Weiser
Assistant Director, Technology Services

## Slide 21: Technology Bond Funding

## Slide 22: Intelligent Classrooms
iTAC (Instructional Technology Advisory Committee) completed their meetings.
  Identified 3 instructional technology tools for the Intelligent Classroom Project
    Mounted Short Throw Projector (digital display)
    Document Camera
    Classroom Audio Amplification System

## Slide 23: Wide Area Network (WAN) Connection
All comprehensive high schools have faster (gigabit) connections installed. All school sites are “in process” of ATT installation.
  Bradley, AHS, CCMS, Rolling Hills, WHS, Mintie, Pajaro Middle, New School, AVCI, and Aptos Jr. have a physical fiber cable for Gig installed but circuits are not yet tested and turned up.
  PV High, Lakeview, and EA Hall have been tested and are now up.
AT&T working to complete all site installations by the end of the school year

## Slide 24: Network Equipment
Erate funding $800,000 of Data Center (NOC) upgrade and installation
Bond funds will be used to fund the “ineligible” school’s share (cost allocate 25% for Northern area schools)
  Exchange Email Server
  Web Content Filter
  Firewall
  Core Network Infrastructure
  Backup
  Storage
  Etc.
Bond funds to be used to support non-Erate eligible items
  UPS battery Backups – 3 Phase
  Fire Suppression
  Cooling
  Facilities Enhancement
  Emergency Generator
  Etc.
Data Center upgrade completion date estimate: Summer 2014

## Slide 25: Data Drops
Completed Bradley Elementary school full network upgrade phase 1.
Erate funding $750,000 for additional data drops and switches at 16 schools in the district
Bond funds to be used to provide additional data drops and switches for the other PVUSD schools and facilities
Schools that have received extra data ports this year via the above funding sources:
  Ann Soldo, Starlight, Landmark, AVCI, EA Hall, Amesti, Freedom, Mintie White, AHS (complete)
  Hall, Calabasas, Hyde, MacQuiddy, Alianza, WHS, PVHS (in process now)

## Slide 26: VDI, NAC, VoIP, Site Video Surveillance
On hold until the completion of the Data Center (NOC).
Hired Senior Applications Analyst 50% bond funded to help move these projects forward.

## Slide 27: Endowment Funds
$500,000/year
Encourage Equity, Refresh and Innovation
This Year: Equity & Refresh
  New Labs in Northern Area Schools
This Year: Innovation
½ Funded ToSA for Professional Development
Pajaro Middle - Class iPads for 24/7 (year 2 & Refresh)
Ann Soldo - Class ChromeBooks 24/7 (year 2 & Refresh)
Lakeview - Supplemental ChromeBooks for 24/7 (year 1)
Innovation Grants (27/7) -Two Class sets of ChromeBooks
  Landmark, Ann Soldo,
Innovation Grants (24/7) - Four Class Sets of iPads
  Calabasas, HA Hyde, Mar Vista, Radcliff
Winter Institute : 2 Sets of 10 Chromebooks w/ Storage and charging lockers – Location TBD
Beginning planning for next year’s Endowment funds, 1 to 1 chrome book projects.

## Slide 28
Next CBOC Meeting
Date : June 10, 2014
Where: District Office
Projects the District did not work on!